## Slide 1
Richmond Rising
Collaborative Stakeholder Committee (CSC)
May 1, 2024

## Slide 2
Project lead for City of Richmond
Project lead for GRID Alternatives
Project lead for Groundwork Richmond
Project lead for Rich City Rides
Project lead for Trust for Public Land
Project lead for UC Berkeley
Project lead for Urban Tilth
Roll Call

## Slide 3
Every first Wednesday of the month 6:00 – 8:00 pm.
In-person Attendance: Nevin Community Center 598 Nevin Ave, Richmond, CA 94801
Virtual Attendance: https://ci-richmond-ca-us.zoom.us/webinar/register/wn_gx8xwknptcutbnefzdbv1w
Phone Attendance: (669) 900-6833, or (669) 444-9171 Webinar ID: 976 6319 9451
All Committee members and members of the public must abide by the Community Agreements
Meeting Information

## Slide 4
While Richmond Rising seeks to strengthen the economy, improve public health and the environment – particularly in the Iron Triangle, Santa Fe and Coronado Neighborhoods, we do so with the awareness that we occupy unceded Huichin and Karkin Ohlone territory.
We acknowledge that land theft of indigenous homelands, and the dismantling of indigenous sovereignty, was done to advance colonization.
We acknowledge that capitalism and white supremacy are branches of colonization that have persisted throughout hundreds of years of oppression, are alive today, and contribute to keeping Black, Indigenous, and all other People of Color from thriving.
We further acknowledge that this country’s political economy and social institutions were built on the forced labor of African people on stolen land through violent, systematic abduction from their homelands and enslavement over hundreds of years.
Land Acknowledgement

## Slide 5
We further acknowledge the exploitation of immigrant and refugee communities as modern forms of cheap and disposable labor are regularly carried out on stolen land.
Thus, we acknowledge that we have been impacted and harmed by these histories and experiences imposed on our ancestors and communities. We further uplift the shared struggle among Black, Indigenous, and All People of Color.
We also acknowledge that indigenous people continue to live here, steward the land, and resist settler colonialism.
We conclude that our Land acknowledgement is an active and evolving statement and process. It requires us to recognize historical injustices and invites us in to be active participants in our collective healing.
Land Acknowledgement

## Slide 6
The City of Richmond and 6 local organizations (together known as ‘Richmond Rising’) received $35 million to bring health, economic, and environmental benefits to the Iron Triangle, Santa Fe, and Coronado neighborhoods.
Richmond Rising is supported by the California Strategic Growth Council’s Transformative Climate Communities Program.
Richmond Rising

## Slide 7
Provides guidance on project implementation and holds us accountable in reaching our goals
Can make recommendations, provide input, and assist Project Leads in implementing project activities
Does not have final decision-making authority
Project Leads must consider recommendations from the Committee and members of the public
Collaborative Stakeholder Committee

## Slide 8
This is the space for members of the public to provide public comment on items that are not included in the agenda.
Public Comment Not on the Agenda

## Slide 9
Each partner will share up-to-date financials and grant expenditures to date for each project and this will be shared with the Committee and the public.
Project Status Reports

## Slide 10
Work completed since last meeting:
  Executed contracts/ agreements with partners (6/6): Grid Alternatives, Groundwork Richmond, Trust for Public Land, Rich City Rides, Urban Tilth, UC Berkeley.
  Hiring of TCC Staff (2/2): Posted, interviewed, hired, and recruited TCC Project Coordinator and TCC Analyst.
  Agreements approved by City Council Approval: Strategic Growth Council Implementation Technical Assistance Grant.
  CSC Meeting: Scheduled, coordinated, and currently facilitating CSC meetings 1-3, including translation, refreshments, and childcare.
  Invoices and Reports: Submitted bimonthly invoice and progress reports 1, 2, 3 & 4. Invoice 1, 2 & 3 have been approved by SGC. First reimbursement check received.
Total expenditures reported to date: $135,451.06
Remaining budget: $558,224.60
Planned work in the next ~two weeks:
  CSC Meeting: Circulating CSC meeting #3 minutes.
  Invoice and Reports: Respond to SGC questions on Invoice 4.
  Leverage Reports: Share forms to report leverage for City and partners.
  Payments: Processing and paying invoices from partners.
Grantee

## Slide 11
Work completed since last meeting:
  Prepared Request for Proposals (RFP) for Neighborhood Complete Streets project.
  Submitted plans to professional civil design services.
  Received and reviewed CSW proposal to support development of the grant.
  CIP Manager reviewed Design Proposal and requested changes to the consultants, CSW-ST2.
  CSW-ST2 updated Design Proposal was approved to start work.
Total expenditures reported to date: $ 6,315.12
Remaining budget: $ 5,174,858.03
Planned work in the next ~two weeks:
  Set up Project Kick-Off meeting.
  Schedule stakeholder meeting this month and have CSW set up community
  meeting with RNC
Neighborhood Complete Streets

## Slide 12
Work completed since last meeting:
  Contract negotiations are still ongoing between TPL and PlaceWorks, but are planned to conclude soon.
  Initial meetings and discussions around the community engagement strategy has begun for the project.
Total expenditures reported to date: $ 22,247.44
Remaining budget: $ 4,793,906.16
Planned work in the next ~two weeks:
  Finalize contract with the landscape architect.
  Develop a draft community engagement plan.
Richmond Wellness Trail

## Slide 13
Work completed since last meeting:
  Continue preparation of design and construction documents.
  Prepare for TCC Kick-off event on April 20.
  Completed Bi-monthly invoicing and progress reports
Total expenditures reported to date: $ 63,692.36
Remaining budget: $ 2,397,395.63
Planned work in the next ~two weeks:
  Prepare for presentation Design Review Board for project approval.
  Post/Interview Candidates for TCC Youth Fellow Program Manager Position.
  Hire a TCC Youth Fellows TCC Youth Fellow Program Manager Position.
  Outreach and promote at the City of Richmond 5 de Mayo Event.
  Received pricing for Solar Panel System –to comply with Leed Requirements of future eBLL building.
  Create O&M Agreement for e-BLL
eBike Lending Library

## Slide 14
Work completed since last meeting:
  2 complete client project
  20 energy efficiency clients
  6 outreach events conducted
  3 outreach events conducted
  Participatedi in TCC Earth Day Event
Total expenditures reported to date: $ 115,490.91
Remaining budget: $ 6,851,205.00
Planned work in the next ~two weeks:
  3 Solar Projects scheduled
  Resilient Homes Team Internal training set for May 9
Resilient Homes

## Slide 15
Work completed since last meeting:
  New Water Conservation apprentices integrated with UT team – supporting Water Conservation installations and creek restoration work.
  First water efficiency improvements installed for Richmond homeowners!
    Primarily focused on drip irrigation for vegetable beds, so far.
Total expenditures reported to date: $ 126,049.77
Remaining budget: $ 1,554,654.01
Planned work in the next ~two weeks:
  Hoping to find our first resident interested in laundry-to-landscape greywater recycling installation at their home.
    Hiring greywater outreach coordinator, hopefully at some point in May.
  Developing our expertise / potentially receiving certification for all staff in Water Catchment.
Basins of Relations

## Slide 16
Work completed since last meeting:
  Continued to work on Adopt-a-Tree canvassing with our Workforce/tree crew.
  Completed Invoicing/reporting for this period.
  Participated in Richmond Rising kick-off celebration on Earth Day; received 12 new tree adoptees.
Total expenditures reported to date: $ 40,606.11
Remaining budget: $ 1,047,406.64
Planned work in the next ~two weeks:
  Continue to attend neighborhood council meetings,
  Contact adoptees, schedule site visits
Bosque del Barrio

## Slide 17
Work completed since last meeting:
Attended the TCC Kick-off event on April 20.
Drafting of construction documents
Met with City regarding procurement process
Total expenditures reported to date: $ 32,577.81
Remaining budget: $ 922,466.19
Planned work in the next ~two weeks:
  Plan final garden design unveiling to the community
  Update project schedule for extension request
  Finalize construction documents
ADA Accessible Garden

## Slide 18
Work completed since last meeting:
  Attended TCC Kick Off Event on April 20th and distributed fruit trees
  Continued fruit tree pick-ups for the project area
  Training the gleaner coordinator
Total expenditures reported to date: $ 48,341.49
Remaining budget: $ 1,119,872.14
Planned work in the next ~two weeks:
  Finalize training curriculum after feedback review
  Begin drafting up summer training application form
  Develop a schedule and outline for the 6-week training program
  Create outreach material for the summer training program
Orchard for ALL!

## Slide 19
Work completed since last meeting:
  Wrapped up invoice 4 (woo hoo!)
  Developed preliminary plan for project expansion to 200+ vegetable box prescriptions
  Onboarded new VeggieRx Project Manager
Total expenditures reported to date: $ 155,324.77
Remaining budget: $ 3,083,547.23
Planned work in the next ~two weeks:
  Training new VeggieRx Project Manager
  Begin working on readiness for Task 4 – Climate Friendly Diet
Veggie Rx

## Slide 20
Work completed since last meeting:
  Continued work with community-based organizations
  Launched the eBike system / Ribbon cutting ceremony
  Trained hired staff
  In the process of hiring a Community Manager to work with stakeholders and the community
  Completed a Community Outreach and Engagement Plan for implementation
Total expenditures reported to date: $ 0
Remaining budget: $ 998,979.21
Planned work in the next ~two weeks:
  Place additional bikes throughout the City at identified locations.
E-Bike Share

## Slide 21
Work completed since last meeting:
  Presentation to Iron Triangle and Santa Fe Neighborhood Councils
  Earth Day Event and Richmond Rising Kick – Off
  Website finished: www.richmondrisingca.org
  Social media accounts launched:
Total expenditures reported to date: $ 55,006.41
Remaining budget: $ 2,511,026.32
Planned work in the next ~two weeks:
  Outreach Social media
Community Engagement Plan

## Slide 22
Work completed since last meeting:
  Updated blue dot data base
  Geofencing for the TCC Area
  Sending messages to test the communication software within the project area
  April 28th – Placement for Small Business Week, Civic Center Plaza
  Reviewed Draft ADU Toolkit and Checklist have been sent to the State for review
Total expenditures reported to date: $ 82,062.44
Remaining budget: $ 599,573.18
Planned work in the next ~two weeks:
  Levying taxes for the Downtown Richmond Property Business Improvement District (DRPBID)
  Quarterly update of the bludot database with Business Information
Displacement Avoidance Plan
Notes: The levying of taxes for DRPBID is applicable to many parcels in the downtown area. The money goes to improving the Downtown area and is also the budget for Richmond Main Street Initiative.

## Slide 23
Work completed since last meeting:
  GRID Alternatives has hired a Solar Trainer to lead their training program
  City of Richmond released RFP for consultant to develop a Place-Based Workforce Development Strategy and Implementation Plan (responses due May 15th)
Total expenditures reported to date: $ 6,560.66
Remaining budget: $ 1,427,247.08
Planned work in the next ~two weeks:
  GRID Alternatives will be onboarding their new Solar Trainer (start date 5/6)
  City of Richmond to begin evaluation of RFP responses after May 15th.
Workforce Development and Economic Opportunity Plan (WDEOP)

## Slide 24
Work completed since last meeting:
  Meetings with project partners to discuss indicators and reporting timelines
  Updated project indicators
  Updated CARB data tracking
  Implemented report feedback
Total expenditures reported to date: $ 0
Remaining budget: $ 1,070,000
Planned work in the next ~two weeks:
  Complete meetings with project partners
  Map reporting timelines across all projects
  Begin drafting a plan for reporting process
Indicator Tracking Plan

## Slide 25
Report out on any community questions or comments received, including responses
Report on Public Comments & Questions

## Slide 26
Committee Bylaws
Nomination Process for Community Seats
Public Kickoff Reflection
Review Project Area Map
Best Practices for Outreach
Indicator Tracking Plan Reporting
Committee Business Items for Discussion

## Slide 27
Review and consider approval of draft bylaws
Committee Bylaws

## Slide 28
Review of nomination form
Review of Recruitment Plan
Nomination Process for Community Seats

## Slide 29
Review and reflect on Earth Day Richmond Rising Public Kickoff
Public Kickoff Reflection

## Slide 30
https://experience.arcgis.com/experience/28d54775eb8b4eceae038f123d9897c0/
Review Project Area Map
Notes: New image for splash window (Waiting for an image to be sent to me)
Add images to pop-ups for project locations
Add school parcels to parcel layer
Correct location of e-bike charging station.
Remove use code from address pop-ups

## Slide 31
General discussion on outreach practices of each organization
Update on Youth Fellows and Climate Health Promoters as Outreach Support
Project-Level Discussion on Best Practices for Outreach

## Slide 32
UC Berkeley is working with individual organizations for Evaluation and Indicator Tracking Plan Reporting
Indicator Tracking Plan Reporting

## Slide 33
Agenda Requests for Next Meeting

## Slide 34
CSC Members, members of the public, and other partners or organizations are encouraged to share information or announcements related to upcoming events, projects, or programs in the Project Area
General Announcements

## Slide 35
Meeting Adjourned
Thank You!
Questions? Comments?
Please reach out at tcc@ci.richmond.ca.us