## Slide 1
Richmond Rising
Collaborative Stakeholder Committee (CSC)
June 5, 2024

## Slide 2
Project lead for City of Richmond
Project lead for GRID Alternatives
Project lead for Groundwork Richmond
Project lead for Rich City Rides
Project lead for Trust for Public Land
Project lead for UC Berkeley
Project lead for Urban Tilth
Roll Call

## Slide 3
Every first Wednesday of the month 6:00 – 8:00 pm.
In-person Attendance: Nevin Community Center 598 Nevin Ave, Richmond, CA 94801
Virtual Attendance: https://ci-richmond-ca-us.zoom.us/webinar/register/wn_gx8xwknptcutbnefzdbv1w
Phone Attendance: (669) 900-6833, or (669) 444-9171 Webinar ID: 976 6319 9451
All Committee members and members of the public must abide by the Community Agreements
Meeting Information

## Slide 4
While Richmond Rising seeks to strengthen the economy, improve public health and the environment – particularly in the Iron Triangle, Santa Fe and Coronado Neighborhoods, we do so with the awareness that we occupy unceded Huichin and Karkin Ohlone territory.
We acknowledge that land theft of indigenous homelands, and the dismantling of indigenous sovereignty, was done to advance colonization.
We acknowledge that capitalism and white supremacy are branches of colonization that have persisted throughout hundreds of years of oppression, are alive today, and contribute to keeping Black, Indigenous, and all other People of Color from thriving.
We further acknowledge that this country’s political economy and social institutions were built on the forced labor of African people on stolen land through violent, systematic abduction from their homelands and enslavement over hundreds of years.
Land Acknowledgement

## Slide 5
We further acknowledge the exploitation of immigrant and refugee communities as modern forms of cheap and disposable labor are regularly carried out on stolen land.
Thus, we acknowledge that we have been impacted and harmed by these histories and experiences imposed on our ancestors and communities. We further uplift the shared struggle among Black, Indigenous, and All People of Color.
We also acknowledge that indigenous people continue to live here, steward the land, and resist settler colonialism.
We conclude that our Land acknowledgement is an active and evolving statement and process. It requires us to recognize historical injustices and invites us in to be active participants in our collective healing.
Land Acknowledgement

## Slide 6
The City of Richmond and 6 local organizations (together known as ‘Richmond Rising’) received $35 million to bring health, economic, and environmental benefits to the Iron Triangle, Santa Fe, and Coronado neighborhoods.
Richmond Rising is supported by the California Strategic Growth Council’s Transformative Climate Communities Program.
Richmond Rising

## Slide 7
Provides guidance on project implementation and holds us accountable in reaching our goals
Can make recommendations, provide input, and assist Project Leads in implementing project activities
Does not have final decision-making authority
Project Leads must consider recommendations from the Committee and members of the public
Collaborative Stakeholder Committee

## Slide 8
This is the space for members of the public to provide public comment on items that are not included in the agenda.
Public Comment Not on the Agenda

## Slide 9
Members to review and approve previous meeting minutes
Review and Approve Previous Meeting Minutes

## Slide 10
Each partner will share up-to-date financials and grant expenditures to date for each project and this will be shared with the Committee and the public.
Project Status Reports

## Slide 11
Work completed since last meeting:
  Executed contracts/ agreements with partners (6/6): Grid Alternatives, Groundwork Richmond, Trust for Public Land, Rich City Rides, Urban Tilth, UC Berkeley.
  Hiring of TCC Staff (2/2): Posted, interviewed, hired, and recruited TCC Project Coordinator and TCC Analyst.
  Agreements approved by City Council Approval: Strategic Growth Council Implementation Technical Assistance Grant.
  CSC Meeting: Scheduled, coordinated, and currently facilitating CSC meetings 1-4, including translation, refreshments, and childcare.
  Invoices and Reports: Calendar for Invoice 5 submitted. Submitted bimonthly invoice and progress reports 1, 2, 3 & 4. Invoice 1, 2 & 3 have been approved by SGC. First and second reimbursement checks received.
Total expenditures reported to date: $135,451.06
Remaining budget: $558,224.60
Planned work in the next ~two weeks:
  CSC Meeting: Circulating CSC meeting #4 minute.
  Invoice and Reports: Start integrating Invoice 5.
  Leverage Reports: Share forms to report leverage for City and partners.
  Payments: Processing and paying invoices from partners.
Grantee

## Slide 12
Work completed since last meeting:
  Project Kick-Off meeting.
Total expenditures reported to date: $ 6,315.12
Remaining budget: $ 5,174,858.03
Planned work in the next ~two weeks:
  Schedule stakeholder meeting this month and have CSW set up community meeting with RNC.
Neighborhood Complete Streets

## Slide 13
Work completed since last meeting:
  Project Kick-Off Meeting with City, PlaceWorks, & stakeholders
  Early conversations & planning around Community Engagement
Total expenditures reported to date: $ 22,247.44
Remaining budget: $ 4,793,906.16
Planned work in the next ~two weeks:
  Plan Coordination meetings with project partners & stakeholders
  Continue planning the project's Community Engagement
  Schedule project site walk
  Schedule survey & site analysis work
Richmond Wellness Trail

## Slide 14
Work completed since last meeting:
Total expenditures reported to date: $ 63,692.36
Remaining budget: $ 2,397,395.63
  Outreach at City of Richmond Pride Event
  Leverage Funding.
  Reached out to local Muralist
Planned work in the next ~two weeks:
  Submit Final Plans for permit
  Present to Art and Culture Commision
  Present to Design Review Board
  Hire TCC Project Manager
  Outreach at City of Richmond Juneteeth event and 5k Event
eBike Lending Library

## Slide 15
Work completed since last meeting:
  2 complete client project
  20 energy efficiency clients
  6 outreach events conducted
  3 outreach events conducted
  Resilient Homes Team Internal training set for May 9
Total expenditures reported to date: $ 115,490.91
Remaining budget: $ 6,851,205.00
Planned work in the next ~two weeks:
  3 Solar Projects scheduled
Resilient Homes

## Slide 16
Work completed since last meeting:
  Installed 5 drip irrigation systems and 1 laundry-to-landscape greywater system for Iron Triangle homeowners!
    Work is supported by our new Water Conservation team, as well as members of our Watershed Restoration Field Crew.
Total expenditures reported to date: $ 126,049.77
Remaining budget: $ 1,554,654.01
Planned work in the next ~two weeks:
  Onboarding new community outreach coordinator
  Several site visits and installations planned.
    Hoping to find more homeowners interested in greywater systems, but not every home is a good fit for this technology.
Basins of Relations

## Slide 17
Work completed since last meeting:
  Planted 20 trees in the designated neighborhoods,
  Continued to canvass and obtain new adoptees,
  Followed up on 30 pending planting sites.
  Attended the City's Career Fair last month to recruit for our Youth Programming and also promote our Adopt-A-Tree Program.
Total expenditures reported to date: $ 40,606.11
Remaining budget: $ 1,047,406.64
Planned work in the next ~two weeks:
  Summer Green Team starts mid-June,
  Canvassing on Fridays,
  Attend Juneteenth event on the 22nd.
  Submit all necessary paperwork for invoice due June 10th.
Bosque del Barrio

## Slide 18
Work completed since last meeting:
  We are still getting utility information for the project and finalizing construction documents
  Monthly project coordination meeting for project status and updates
Total expenditures reported to date: $ 32,577.81
Remaining budget: $ 922,466.19
Planned work in the next ~two weeks:
  June 13th, 2024 presentation at Arts and Culture Commission Meeting
  June 14th, 2024 at Unity Park Plaza ADA Garden Design Unveiling
ADA Accessible Garden

## Slide 19
Work completed since last meeting:
  Developed a 6-week training program schedule for the summer Gleaning Apprenticeship
  Summer Gleaning Apprenticeship application posted online at urbantilth.org
  Created outreach material for the training program
  Published social media post highlighting the "Orchard For All!" Program in the project area
Total expenditures reported to date: $ 48,341.49
Remaining budget: $ 1,119,872.14
Planned work in the next ~two weeks:
  Review Applications for Summer Training Program
  Begin Scheduling interviews for program start date July 1st, 2024
Orchard for ALL!

## Slide 20
Work completed since last meeting:
  Launched Climate Health Promoter Training cohort 1!
Total expenditures reported to date: $ 155,324.77
Remaining budget: $ 3,083,547.23
Planned work in the next ~two weeks:
  1st cohort graduates
  Community Health Conductor (x2) job description and opening announcement
Veggie Rx

## Slide 21
Work completed since last meeting:
  Continued work with community-based organizations
  Completed a Community Outreach and Engagement Plan for implementation
  Started a survey to select 2 out of 5 bike hub locations
Total expenditures reported to date: $ 0
Remaining budget: $ 998,979.21
Planned work in the next ~two weeks:
  Place additional bikes throughout the City at identified locations.
E-Bike Share

## Slide 22
Work completed since last meeting:
  Website updated: www.richmondrisingca.org
  City Manager's Weekly Report for CSC recruitment
  Attended and tabled at:
    Park RX Event
    5 de mayo
    Nystrom & Coronado 6th Grade Graduation Party
Total expenditures reported to date: $ 55,006.41
Remaining budget: $ 2,511,026.32
Planned work in the next ~two weeks:
Attend and table at:
  Community Housing Development Corporation’s (CHDC) Community Awareness Day
BTA Grand Reopening
  Juneteenth
Community Engagement Plan

## Slide 23
Work completed since last meeting:
  Updated blue dot data base
  Geofencing for the TCC Area
  Sending messages to test the communication software within the project area
  April 28th – Placement for Small Business Week, Civic Center Plaza
  Reviewed Draft ADU Toolkit and Checklist have been sent to the State for review
Total expenditures reported to date: $ 82,062.44
Remaining budget: $ 599,573.18
Planned work in the next ~two weeks:
  Levying taxes for the Downtown Richmond Property Business Improvement District (DRPBID)
  Quarterly update of the bludot database with Business Information
Displacement Avoidance Plan
Notes: The levying of taxes for DRPBID is applicable to many parcels in the downtown area. The money goes to improving the Downtown area and is also the budget for Richmond Main Street Initiative.

## Slide 24
Work completed since last meeting:
  City of Richmond released RFP for consultant to develop a Place-Based Workforce Development Strategy and Implementation Plan and 1 response was submitted by May 15th.
  The proposal was reviewed and is in process of going to City Council for approval.
Total expenditures reported to date: $ 6,560.66
Remaining budget: $ 1,427,247.08
Planned work in the next ~two weeks:
  City of Richmond to begin going to City Council on June 25th.
Workforce Development and Economic Opportunity Plan (WDEOP)

## Slide 25
Work completed since last meeting:
  Completed meetings with all project partners to discuss indicators
  Updated indicator tables
  Developed logic models for each project
  Completed a final draft of the report to be shared with project partners for feedback
Total expenditures reported to date: $ 0
Remaining budget: $ 1,070,000
Planned work in the next ~two weeks:
  Share report and wait for feedback
  Implement feedback and submit final version of the report
  Launch new CGHC website! RR will be featured and report posted
Indicator Tracking Plan

## Slide 26
Report out on any community questions or comments received, including responses
Report on Public Comments & Questions

## Slide 27
Community Seat Nomination
Strategic Growth Council Contract Amendment
Community Engagement Updates
Annual Reports to City Council and SGC
Postpone July Meeting for Holiday
Committee Business Items for Discussion

## Slide 28
Review community seat applications and consider nomination of community members to CSC
Discuss how partners have engaged community to advertise these positions
Community Seat Nomination

## Slide 29
Update on extension workbooks
SGC Contract Amendment Status

## Slide 30
Project-level community engagement updates
Continue discussion from May CSC regarding individual and collective engagement practices
Community Engagement Updates

## Slide 31
Discuss requirements and Project Lead questions in preparation for larger discussion at July CSC meeting
Annual Reports to City Council and SGC

## Slide 32
Ride Today Survey

## Slide 33
Given July 4th holiday, consider rescheduling July CSC meeting to July 10th
Postpone July Meeting for Holiday

## Slide 34
Agenda Requests for Next Meeting

## Slide 35
CSC Members, members of the public, and other partners or organizations are encouraged to share information or announcements related to upcoming events, projects, or programs in the Project Area
General Announcements

## Slide 36
Meeting Adjourned
Thank You!
Questions? Comments?
Please reach out at tcc@ci.richmond.ca.us