## Slide 1
Richmond Rising
Collaborative Stakeholder Committee (CSC)
August 7, 2024

## Slide 2
Project lead for City of Richmond
Project lead for GRID Alternatives
Project lead for Groundwork Richmond
Project lead for Rich City Rides
Project lead for Trust for Public Land
Project lead for UC Berkeley
Project lead for Urban Tilth
Roll Call

## Slide 3
Every first Wednesday of the month 6:00 – 8:00 pm.
In-person Attendance: Nevin Community Center 598 Nevin Ave, Richmond, CA 94801
Virtual Attendance: https://ci-richmond-ca-us.zoom.us/webinar/register/wn_gx8xwknptcutbnefzdbv1w
Phone Attendance: (669) 900-6833, or (669) 444-9171 Webinar ID: 976 6319 9451
All Committee members and members of the public must abide by the Community Agreements
Meeting Information

## Slide 4
While Richmond Rising seeks to strengthen the economy, improve public health and the environment – particularly in the Iron Triangle, Santa Fe and Coronado Neighborhoods, we do so with the awareness that we occupy unceded Huichin and Karkin Ohlone territory.
We acknowledge that land theft of indigenous homelands, and the dismantling of indigenous sovereignty, was done to advance colonization.
We acknowledge that capitalism and white supremacy are branches of colonization that have persisted throughout hundreds of years of oppression, are alive today, and contribute to keeping Black, Indigenous, and all other People of Color from thriving.
We further acknowledge that this country’s political economy and social institutions were built on the forced labor of African people on stolen land through violent, systematic abduction from their homelands and enslavement over hundreds of years.
Land Acknowledgement

## Slide 5
We further acknowledge the exploitation of immigrant and refugee communities as modern forms of cheap and disposable labor are regularly carried out on stolen land.
Thus, we acknowledge that we have been impacted and harmed by these histories and experiences imposed on our ancestors and communities. We further uplift the shared struggle among Black, Indigenous, and All People of Color.
We also acknowledge that indigenous people continue to live here, steward the land, and resist settler colonialism.
We conclude that our Land acknowledgement is an active and evolving statement and process. It requires us to recognize historical injustices and invites us in to be active participants in our collective healing.
Land Acknowledgement

## Slide 6
The City of Richmond and 6 local organizations (together known as ‘Richmond Rising’) received $35 million to bring health, economic, and environmental benefits to the Iron Triangle, Santa Fe, and Coronado neighborhoods.
Richmond Rising is supported by the California Strategic Growth Council’s Transformative Climate Communities Program.
Richmond Rising

## Slide 7
Provides guidance on project implementation and holds us accountable in reaching our goals
Can make recommendations, provide input, and assist Project Leads in implementing project activities
Does not have final decision-making authority
Project Leads must consider recommendations from the Committee and members of the public
Collaborative Stakeholder Committee

## Slide 8
This is the space for members of the public to provide public comment on items that are not included in the agenda.
Public Comment Not on the Agenda

## Slide 9
Members to review and approve previous meeting minutes
Review and Approve Previous Meeting Minutes

## Slide 10
Each partner will share up-to-date financials and grant expenditures to date for each project and this will be shared with the Committee and the public.
Project Status Reports

## Slide 11
Work completed since last meeting:
  CSC Meeting: Scheduled, coordinated, and currently facilitating CSC meeting #9, including translation, refreshments, and childcare.
  Invoices and Reports: Began collecting Invoice and Progress Report#6, for months of June and July. Submitted corrections to bimonthly invoice and progress reports #5. Received and began disbursing check #4.
Total expenditures reported to date: $ 191,643.09
Remaining budget: $ 502,032.57
Planned work in the next ~two weeks:
  Fully distribute Check # 4
  Review and share feedback on Invoice and Progress Report #6
Grantee

## Slide 12
Work completed since last meeting:
  Began coordination for application for US Department of Transportation Reconnecting Communities Pilot Program, including submission of request for Letter of Support from Caltrans.
Total expenditures reported to date: $ 8,121.28
Remaining budget: $ 5,173,051.87
Planned work in the next ~two weeks:
  Fully onboard grantwriting consultants from Trust for Public Land
  Begin ongoing check-ins to prepare application due September 30th
Neighborhood Complete Streets

## Slide 13
Work completed since last meeting:
  Base maps have been produced and PlaceWorks has begun site analysis of the project area
  Project Site Walk
    Consultants: PlaceWorks (Landscape Architect) & CSW (Engineer)
    Agency: City of Richmond (TCC, Public Works, Neighborhood Complete Streets)
    Partners: Groundwork Richmond & National Parks Service
  Outreach & Tabling: We Run Richmond 5k Event with Rich City Rides & Groundwork Richmond
    Est. 15 people stopped by, 6 people signed up for Richmond Wellness Trail updates
  Researching additional funding sources in partnership with COR/Neighborhood Complete Streets
Total expenditures reported to date: $ 31,127.12
Remaining budget: $ 4,785,026.48
Planned work in the next ~two weeks:
  Ongoing planning & design work
Richmond Wellness Trail

## Slide 14
Work completed since last meeting:
Total expenditures reported to date: $ 99,128.48
Remaining budget: $ 2,361,923.51
Planned work in the next ~two weeks:
  Present building design at design review board.
eBike Lending Library

## Slide 15
Work completed since last meeting:
Hired on SolarCorps Fellow and Rising Sun Extern
City of Richmond/ GRID Alternatives Solar Programs Workshop
5500 resident mailing sent to Richmond Ciy Residents
Participated at RYSE Center's National Night Out Event
Sent mass mailing to 1700 Contra Costa residents
20 clients contracted for solar.
  Total expenditures reported to date: $ 150,415.11
  Remaining budget: $ 6,816,280.80
Planned work in the next ~two weeks:
August 21st Client Workshop at GRID's office in Oakland 6-8pm
Resilient Homes

## Slide 16
Work completed since last meeting:
  Outreach to homeowners to inform residents about water conservation offerings, focusing on area around Richmond Wellness Trail.
  Two more drip irrigation systems installed, with appx 20,000 gallons of annual water savings.
    Total number of systems installed during grant period: 12
Total expenditures reported to date: $ 146,325.22
Remaining budget: $ 1,534,378.56
Planned work in the next ~two weeks:
  Hoping to find more homeowners interested in laundry-to-landscape greywater recycling, specifically.
  Continued outreach, site visits, and installations of water conservation systems for Richmond homeowners.
Basins of Relations

## Slide 17
Work completed since last meeting:
  Planted 31 new trees for the month of July, 59 to date
  Continue to canvass Santa Fe, Coronado, and Iron Triangle neighborhoods
  Tabled at the 5k run
  Walk through for Wellness Trail phase 2
  Attended monthly UFAC meeting
Total expenditures reported to date: $ 80,072.72
Remaining budget: $ 1,007,940.00
Planned work in the next ~two weeks:
  Plant more trees
  Continue canvassing
  Coordinate Arbor Day event
Bosque del Barrio

## Slide 18
Work completed since last meeting:
  Design and construction documents are 90% complete and the project will be presented to the Design Review Board on August 14th for final acceptance.
  Utility service and connection details have been determined and coordinated with the adjacent e-bike Lending Library project.
  The approach to the Public Art has been discussed, estimated, and will be presented to the Arts and Culture Commission in September or October for acceptance of the concept and approach.
Total expenditures reported to date: $ 38,072.75
Remaining budget: $ 916,246.00
Planned work in the next ~two weeks:
  Submit to plans to City for permitting in mid-August.
  Prepare bid documents and solicit contractor pricing in September/October
ADA Accessible Garden

## Slide 19
Work completed since last meeting:
  Conducting Orchard for All! Gleaners 6-week training program
  Canvassed the project area to recruit more homeowners with fruit trees
Total expenditures reported to date: $ 67,051.87
Remaining budget: $ 1,101,161.76
Planned work in the next ~two weeks:
  Host training program graduation, present certificates of completion and stipends
  Create annual reports for end of the year
  Bi-monthly invoicing
Orchard for ALL!

## Slide 20
Work completed since last meeting:
  Hired 2 Community Health Promoters to support Task 3 – Train the Trainers Program and Task 4 – Climate Friendly Diet Program
  Distributed 174 VeggieRx produce bags
  Conducted 5 HEAT classes
  Finalized schedule for Community Health Promoter training cohort #2
Total expenditures reported to date: $ 227,190.88
Remaining budget: $ 3,011,681.12
Planned work in the next ~two weeks:
  Organize and draft readiness deliverables for Task 4 – Climate Friendly Diet Program
  Submit leverage fund report and invoice 6
  Finalize annual summary reports for August 31 deadline
Veggie Rx

## Slide 21
Work completed since last meeting:
  Honed invoicing submission process with vendor; approved June invoices for payment
  Continued coordinated outreach and distribution of vouchers
Total expenditures reported to date: $ 361,544.30
Remaining budget: $ 637,434.91
Planned work in the next ~two weeks:
  Continued coordinated outreach
E-Bike Share

## Slide 22
Work completed since last meeting:
  Continued onboarding of Youth Fellows Program Manager
  Began drafting modules and other training materials for Youth Fellows
Total expenditures reported to date: $ 92,735.62
Remaining budget: $ 2,473,297.11
Planned work in the next ~two weeks:
Continue drafting modules and other training materials
Community Engagement Plan

## Slide 23
Work completed since last meeting:
  CLT:
    Fellow is transitioning to separate program; City considering applying for additional Fellow
    Waiting for UCSF Grant Agreement before reporting leveraged time to project
  ADU Toolkit:
    City continuing to review ADU toolkit permit set
    Continued community outreach, including National Night Out
  Buy Local campaign
    Released RFP/Q for an Event/Marketing Consultant for Buy Local Campaign (close date on 8/22)
    Continuing to draft contract with bluedot to support the Buy Local campaign
Total expenditures reported to date: $ 104,562.44
Remaining budget: $ 577,073.18
Planned work in the next ~two weeks:
  RFP for Buy Local campaign
Displacement Avoidance Plan
Notes: The levying of taxes for DRPBID is applicable to many parcels in the downtown area. The money goes to improving the Downtown area and is also the budget for Richmond Main Street Initiative.

## Slide 24
Work completed since last meeting:
  GRID Solar Trainer onboarded and learning IBT200 curriculum and labs. Traveled to an affiliate office for trainer shadowing and train-the-trainer sessions.
  Coordination meeting between GRID and E&T Deputy Director
  CSC Presentation
Total expenditures reported to date: $ 11,370.21
Remaining budget: $ 1,422,437.53
Planned work in the next ~two weeks:
Workforce Development and Economic Opportunity Plan (WDEOP)

## Slide 25
Work completed since last meeting:
  Revised Indicator Tracking & Evaluation Report
  Drafting 2 Case studies: Veggie Rx and Universal Design Garden
  Working on data inputs for CARB evaluation tools
Total expenditures reported to date: $ 0
Remaining budget: $ 1,070,000
Planned work in the next ~two weeks:
  Share Final Evaluation Plan
  Update case studies
  Work on CARB tools
Indicator Tracking Plan

## Slide 26
Report out on any community questions or comments received, including responses
Report on Public Comments & Questions

## Slide 27
Review and make recommendations on nomination forms received by the Committee. Review to occur bimonthly.
CSC Community Member Nominations

## Slide 28
RichmondBUILD cohort
Review and make recommendations on nomination forms received by the Committee. Review to occur bimonthly.

## Slide 29
Youth Fellows Program
Introduction of Youth Fellows Manager and Youth Fellows Program

## Slide 30
Draft Annual Summary to Council
Share draft presentation of Annual Summary to Richmond City Council, including review of template slides for Partners to complete.

## Slide 31
SGC Annual Summary
Review and approve Annual Report to Strategic Growth Council.

## Slide 32
Agenda Requests for Next Meeting

## Slide 33
CSC Members, members of the public, and other partners or organizations are encouraged to share information or announcements related to upcoming events, projects, or programs in the Project Area
General Announcements

## Slide 34
Meeting Adjourned
Thank You!
Questions? Comments?
Please reach out at tcc@ci.richmond.ca.us